## Bug sheet
Bug sheet
| No | Status (new / progress / completed) | Bug found date | Writer | Bug reason | Screen name | responsible person | Corrector | Confirmer | Cause of the bug
sample | 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## Data Definition
Table Name |  | Users
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique | Description
UserId | int | ○ | ○ |  |  | ○
RoleId | int |  | ○ | 2 | Roles
FirstName | nvarchar(50)
SecondName | nvarchar(50)
Username | nvarchar(150) |  | ○ |  |  | ○
Email | nvarchar(150) |  | ○ |  |  | ○
Password | nvarchar(255) |  | ○
ConfirmPassword | nvarchar(255) |  | ○
Address | nvarchar(MAX)
Mobile | nvarchar(50)
Profile | nvarchar(255) |  |  | ~/img/Dashboard/Profile/img_guest.png
Gender | nvarchar(50) |  |  | None
CreatedAt | datetime |  | ○
UpdatedAt | datetime |  | ○
Table Name |  | Roles
Column Name |  | Data Type | PK | NOT NULL | Default | FK | Unique
RoleId |  | int | ○ | ○ |  |  | ○
Role |  | nvarchar(150) |  | ○ |  |  | ○
CreatedAt |  | datetime |  | ○
Table Name |  | Articles
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique | Description
ArticleId | int | ○ | ○ |  |  | ○
UserId | int |  | ○ |  | ○
Title | nvarchar(255) |  | ○
Slug | nvarchar(255) |  | ○ |  |  | ○
Description | nvarchar(MAX) |  | ○
Excerpt | nvarchar(255) |  | ○
CategoryId | int |  | ○ |  | ○
Thumbnail | nvarchar(255)
Status | int
CreatedAt | datetime |  | ○
ReportId | int |  |  |  | ○
ReportStatus | int |  |  | 0
ReportAt | datetime |  | ○
Table Name |  | Photos
Column Name |  | Data Type | PK | NOT NULL | Default | FK | Unique
PhotoId |  | int | ○ | ○ |  |  | ○
ArticleId |  | int |  | ○ |  | ○
PhotoName |  | nvarchar(255) |  | ○
CreatedAt |  | datetime |  | ○
DeleteStatus |  | int |  | ○
Table Name | categories
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique
CategoryId | int | ○ | ○ |  |  | ○
Name | nvarchar(255) |  | ○ |  |  | ○
Slug | nvarchar(255) |  | ○ |  |  | ○
CreatedAt | datetime |  | ○
Table Name | Comments
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique
CommentID | int | ○ | ○ |  |  | ○
UserId | int |  | ○ |  | ○
ArticleId | int |  | ○ |  | ○
Message | nvarchar(MAX) |  | ○
Created At | datetime |  | ○
Updated At | datetime |  | ○
Table Name | Likes
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique
LikeId | int | ○ | ○ |  |  | ○
UserId | int |  | ○ |  | ○
ArticleId | int |  | ○ |  | ○
CreatedAt | datetime |  | ○
Table Name | Reports
Column Name | Data Type | PK | NOT NULL | Default | FK | Unique
ReportId | int | ○ | ○ |  |  | ○
Content | nvarchar(255) |  | ○ |  |  | ○
CreatedAt | datetime |  | ○

## Work flow
|  |  |  | Frontend(design only) |  |  |  |  | Backend
No | Task | Frontend | Backend | Start date | End date | Actual date and hr | Progress | Trainer check | Start date | End date | Actual date and hr | Progress | Trainer check
1 | Login | TZ | TZ | 9.1.2023 | 9.1.2023 | 9.1.2023 - 1 hr | 100% |  | 12.1.2023 | 22.1.2023 | 13.1.2023 - 1hr | 100%
2 | SignUp | AA | TZ | 9.1.2023 | 9.1.2023 | 9.1.2023 - 2 hr and half | 100% |  | 12.1.2023 | 22.1.2023 | 13.1.2023 - 1hr | 100%
3 | Forgot Password | KKPW | TZ | 9.1.2023 | 9.1.2023 | 9.1.2023 - 1hr | 100% |  | 12.1.2023 | 22.1.2023 | 13.1.2023 - 40mins | 100%
4 | Reset Password | KKPW | AA | 9.1.2023 | 9.1.2023 | 9.1.2023 - 1hr | 100% |  | 12.1.2023 | 22.1.2023 | 13.1.2023 - 1hr and half | 100%
5 | middleware for controlling user routes & admin routes | TZ | TZ | [5 empty] | 12.1.2023 | 22.1.2023 | 14.1.2023 - 3hr | 100%
Admin side
6 | create Category(CRUD)
| - create | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 25 mins | 100% |  | 12.1.2023 | 22.1.2023 | 14.1.2023 - 45 mins | 100%
| edit/update/ delete | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 45 mins | 100% |  | 12.1.2023 | 22.1.2023 | 14.1.2023 - 1hr and half | 100%
| list | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 20 mins | 100% |  | 12.1.2023 | 22.1.2023 | 14.1.2023 - 30 mins | 100%
7 | create Articles(CRUD) (From both side of admin and user )
| - create | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 40 mins | 100% |  | 12.1.2023 | 22.1.2023 | 14.1.2023 - 2hr | 100%
| edit/update/Delete | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 40 mins | 100% |  | 12.1.2023 | 22.1.2023 | 15.1.2023 - 1hr | 100%
| list | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 40 mins | 100% |  | 12.1.2023 | 22.1.2023 | 15.1.2023 - 1hr | 100%
8 | AdminDashboard | TZ | TZ,KKPW,AA | 9.1.2023 | 10.1.2023 | 10.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 3hr | 100%
9 | AdminProfile | AA | TZ | 10.1.2023 | 10.1.2023 | 10.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr | 100%
10 | User list | KKPW | TZ | 10.1.2023 | 11.1.2023 | 10.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 35 mins | 100%
11 | AdminPasswordChange | TZ | AA | 10.1.2023 | 11.1.2023 | 11.1.2023 - 40 mins | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr and half | 100%
| User list import with excel | TZ | TZ,KKPW,AA | 10.1.2024 | 11.1.2024 | 10.1.2023 - 5 mins | 100% |  | 12.1.2023 | 22.1.2023 | 17.1.2023 - 2hr | 100%
12 | User list download with excel | TZ | KKPW | 10.1.2025 | 11.1.2025 | 10.1.2023 - 5 mins | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr | 100%
13 | Create Reports(CRUD)
| create | AA | AA | 10.1.2023 | 10.1.2023 | 10.1.2023 - 30 mins | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 45 mins | 100%
| Delete | AA | AA | 10.1.2023 | 10.1.2023 | 10.1.2023 - 30 mins | 100% |  | 12.1.2023 | 22.1.2023 | 21.1.2023 - 25 mins | 100%
| list | AA | AA | 10.1.2023 | 10.1.2023 | 10.1.2023 - 25 mins | 100% |  | 12.1.2023 | 22.1.2023 | 21.1.2023 - 20 mins | 100%
14 | Archieve
| Archieve List | TZ | TZ | 10.1.2023 | 10.1.2023 | 10.1.2023 - 30 mins | 100% |  | 12.1.2023 | 22.1.2023 | 20.1.2023 - 25 mins | 100%
| UnArchieve / Delete | TZ | TZ | 10.1.2023 | 10.1.2023 | 10.1.2023 - 15 mins | 100% |  | 12.1.2023 | 22.1.2023 | 20.1.2023 - 40 mins | 100%
15 | Request Article
| Request article list | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 30 mins | 100% |  | 12.1.2023 | 22.1.2023 | 14.1.2023 - 35 mins | 100%
| Request article detail | TZ,KKPW,AA | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 1hr and half | 100% |  | 12.1.2023 | 22.1.2023 | 15.1.2023 - 1hr and half | 100%
16 | Trend Article
| Show trend article lists | AA | AA | 10.1.2023 | 10.1.2023 | 10.1.2023 - 10 mins | 100% |  | 12.1.2023 | 22.1.2023 | 22.1.2023 - 20 mins | 100%
User side
17 | Home (index page) | TZ,AA,KKPW | TZ,AA,KKPW | 11.1.2023 | 12.1.2023 | 11.1.2023 - 4hr | 100% |  | 12.1.2023 | 22.1.2023 | 18.1.2023 - 2hr | 100%
18 | Search Article | AA,TZ | AA,TZ | 11.1.2023 | 11.1.2023 | 11.1.2023 - 30 mins | 100% |  | 12.1.2023 | 22.1.2023 | 20.1.2023 - 30 mins | 100%
19 | Article Details | KKPW,TZ,AA | KKPW,TZ,AA | 12.1.2023 | 13.1.2023 | 13.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 18.1.2023 - 2hr | 100%
20 | UserDashboard | TZ | TZ,KKPW | 9.1.2023 | 9.1.2023 | 9.1.2023 - 3 hr | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr and half | 100%
21 | UserPasswordChange | TZ | TZ | 10.1.2023 | 10.1.2023 | 10.1.2023 - 1 hr | 100% |  | 12.1.2023 | 22.1.2023 | 16.1.2023 - 50 mins | 100%
22 | User comment | AA | AA,TZ | 12.1.2023 | 13.1.2023 | 13.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 21.1.2023 - 2hr | 100%
23 | User Like | AA | AA,KKPW | 12.1.2023 | 13.1.2023 | 13.1.2023 - 1 day | 100% |  | 12.1.2023 | 22.1.2023 | 20.1.2023 - 3hr | 100%
24 | Waiting Article
| Waiting article list | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 25mins | 100% |  | 12.1.2023 | 22.1.2023 | 15.1.2023 - 34 mins | 100%
| Waiting article list edit/delete | KKPW | KKPW | 10.1.2023 | 10.1.2023 | 10.1.2023 - 18 mins | 100% |  | 12.1.2023 | 22.1.2023 | 15.1.2023 - 1hr | 100%
Form Validation
25 | SignUp |  | TZ | [5 empty] | 12.1.2023 | 22.1.2023 | 13.1.2023 - 2hr and half | 100%
26 | Login |  | TZ | [5 empty] | 12.1.2023 | 22.1.2023 | 13.1.2023 - 1hr and half | 100%
27 | Forgot Password |  | KKPW | [5 empty] | 12.1.2023 | 22.1.2023 | 13.1.2023 - 1hr and half | 100%
28 | Reset Password |  | AA | [5 empty] | 12.1.2023 | 22.1.2023 | 13.1.2023 - 2hr | 100%
29 | EditUserProfile |  | TZ | [5 empty] | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr | 100%
30 | CreateArticle |  | KKPW | [5 empty] | 12.1.2023 | 22.1.2023 | 14.1.2023 - 1half and half | 100%
31 | UpdateArticle |  | KKPW | [5 empty] | 12.1.2023 | 22.1.2023 | 15.1.2023 - 2hr | 100%
32 | CreateCategory |  | KKPW | [5 empty] | 12.1.2023 | 22.1.2023 | 15.1.2023 - 45mins | 100%
33 | UpdateCategory |  | KKPW | [5 empty] | 12.1.2023 | 22.1.2023 | 15.1.2023 - 45 mins | 100%
34 | PasswordSetting |  | TZ,AA | [5 empty] | 12.1.2023 | 22.1.2023 | 16.1.2023 - 1hr | 100%
35 | CreateReport |  | AA | [5 empty] | 12.1.2023 | 22.1.2023 | 16.1.2023 - 25 mins | 100%
36 | UpdateReport |  | AA | [5 empty] | 12.1.2023 | 22.1.2023 | 16.1.2023 - 35 mins | 100%

## Project Planning
No. | Tasks | Durations | Start-Date | Due-Date | Resource Name
| 1. UI Design Prototypes | 2days | 2023-07-01 | 2023-08-01
| 2.Designing the database | 1day | 2023-06-01 | 2023-06-01
| 2. Implementation (Administration side) | 3days for each tasks and members
| 2.1 User Profile+ Dashboard both(User & Admin) |  |  |  | Thein Zan
| 2.2 Categories + Articles |  |  |  | Kay Khine Pyone Wai
| 2.3 UserLists + Reports + Viewers |  |  |  | Aung Aung
| 3. Implementation (User side) | 5days for each tasks and members
| 3.1 Common(Header+Footer) + Category |  |  |  | Thein Zan/ Kay Khine Pyone Wai
| 3.2 Index (Home Page) |  |  |  | Thein Zan/ Kay Khine Pyone Wai/ Aung Aung
| 3.3 Article Detail Page + Search + Related Articles |  |  |  | Thein Zan/ Kay Khine Pyone Wai/ Aung Aung
| 3.4 Like and Comments + Viewers |  |  |  | Thein Zan/ Aung Aung
| 3.5 Pre common testing and debugging |  |  |  | Thein Zan/ Kay Khine Pyone Wai/ Aung Aung
| 4.Unit Testing | 2days for all members
4.1Unit test for each
4.2 Debugging
4.3 Final reveal on the testing
| 5 Final Report | 3days

## Login
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Email | Textbox |  | I | 〇 |  | 50 | blank | Users | email | Check require validation. Check Email Format. Check the email has already had in the database. | Email is required. Email must be valid.
2 | Password | Textbox |  | I | 〇 | 8 | 100 | blank | Users | password | Check require validation. Check both email and password is the same as the one user stored in the server. | Password is required. Email or password is incorrect.
3 | Sign In | Submit |  | O | × | [5 empty] | Go to Dashboard page.
4 | Sign Up | Link Buttom |  | O | × | [5 empty] | Go to Register page.
5 | Forget Password | Link Button |  | O | × | [5 empty] | Go to forgot password page

## User SignUp
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Username | Textbox |  | I | 〇 |  | 50 | blank | Users | username | Check require validation. | Username field required, username is already taken.
2 | Email | Textbox |  | I | 〇 |  | 50 | blank | Users | email | Check require validation. Check Email Format. Check the email has already had in the database. | Email can't blank Email format is invalid Email is already exist
3 | Password | Textbox |  | I | 〇 | 8 | 100 | blank | Users | password | Check require validation. Check min validation | Password name can't blank Password min length is 8 character. Your password must be mininum 8 characters long.Your password should contain at-least 1 Uppercase, 1 Lowercase, 1 Numberic and 1 Special character
4 | Confirm Password | Textbox |  | I | 〇 | 8 | 100 | blank | Users | confirm password | Check require validation. Check whether same or not with password field. | Conrim password name can't blank Conrim password min length is 8 character Password does't match
5 | Sign Up | Submit |  | O | × | [5 empty] | Check validation and if it is ok, insert into users table and directly change the route into login page
6 | Sign In | link Button |  | O | × | [5 empty] | Go to login page.

## AdminDashboard
Dashboard

## CategoryCreate
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Title | Textbox |  | I | 〇 |  | 50 | blank | Categories | Name | Check require validation. Check title is already existed | Category name can't be blank, Category name can't be the same as existing name
2 | Slug | Textbox |  | I | 〇 |  | 50 | blank | Categories | Slug | Check require validation. Check slug is already existed | Category slug can't be the same as existing slug
3 | Create | Submit |  | 〇 | × |  |  | blank |  |  | Check the validation and if it is okay, it will insert into Categories table
Dashboard
Subcategories
Courses
User Lists

## CategoryList
Dashboard
Subcategories
Courses
User Lists
ID
Subcategory Name
Courses
Action

## ArticleCreate
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Title | Textbox |  | I | 〇 |  | 50 | blank | Articles | Title | Check require validation. | Title name can't be blank
2 | Slug | Textbox |  | I | 〇 |  | 50 | blank | Articles | Slug | Check require validation. Check the slug is already existed | Article slug can't be the same as existing slug
3 | Description | Textbox |  | I | 〇 |  | MAX | blank | Articles | Description | Check require validation. | Description can't be blank
4 | Thumbnail | File upload |  | I |  |  |  | blank | Articles | Thumbnail | Check file extension and file length | Only .jpg, .jpeg, .png files are supported, image size should be less than 100KB
5 | Photos | File upload |  | I |  |  |  | blank | Photos | Photo | Check file extension and file length | Only .jpg, .jpeg, .png files are supported, image size should be less than 100KB
6 | Upload | Submit |  | 〇 | × |  |  | blank | Articles |  | Check the validation, if it is okay, it will insert into article's table
Courses
User Lists

## ArticleList
Courses
User Lists
ID
Course Name
Instructor
Action
Subcategory
Price

## UserList
ID
Action
Java, C++,...

## ReportList
ID
Action
Java, C++,...

## ReportCreate
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Title | Textbox |  | I | 〇 |  | 255 | blank | Reports | Content | Check require validation. | Report's message can't be blank
2 | Create | Button |  | 〇 | × |  |  | blank | Reports |  | Check validation, if it is okay, it will insert into report table.
3 | Cancel | Button |  | 〇 | × |  |  | blank | Reports |  | Go to previous page
Courses
User Lists

## AdminProfile
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Username | Textbox |  | I | O |  | 50 | blank | Users | Username | check require validation.check the username is already exists. | Username is already in taken.
2 | Email | Textbox |  | I | O |  | 50 | blank | Users | Email | Check require validation. Check email is already in taken , Check email format is valid or not | Email is already in taken, Email format is invalid.
3 | First Name | Textbox |  | I | O |  | 50 | blank | Users | FirstName | Check require validation. | Name field required
4 | Last Name | Textbox |  | I | O |  | 50 | blank | Users | LastName | Check require validation. | Name field required
5 | Mobile | Textbox |  | I | O |  | 50 | blank | Users | Mobile | Check require validation. Check mobile format is valid or not. | Mobile format is not a valid number, Mobile field required
6 | Address | Textbox |  | I | O |  | 255 | blank | Users | Address | Check require validation. | Address field required
7 | Gender | Dropdown list |  | I | O |  |  | None | Users | Gender | Check require validation. | Choose your gender
8 | Profile image | File Upload |  | I |  |  |  |  | Users | Profile Image | Check the file extension that is .jpg, .jpeg, .png. Check the file length | Only .jpg, .jpeg, .png files are supported. File size should be less than 100kb
9 | Update | Button |  | O |  |  |  | blank |  |  | Check validation and if it is ok, insert into users table.

## UserPasswordChange
№ | Name | Type | Tab IDX | I/O | single item check |  |  | initial value | DB (CRUD) |  | Remarks | Validation message
[5 empty] | Required | Digits
[6 empty] | Min | Max |  | Table Name | Column Name
1 | Old Password | Textbox |  | I | 〇 |  | 50 | blank | Users |  | Check require validation. | User name can't blank
2 | New Password | Textbox |  | I | 〇 | 8 | 100 | blank | Users | password | Check require validation. Check min validation | Password name can't blank Password min length is 8 character
3 | Confirm Password | Textbox |  | I | 〇 | 8 | 100 | blank | Users | confirm password | Check require validation. Check whether same or not with password field. | Conrim password name can't blank Conrim password min length is 8 character Password does't match
4 | Change Password | Button |  | O | × |  |  | blank |  |  | Check validation and if it is ok, insert into users table.
5 | Cancle | Button |  | O | × | [5 empty] | Go to Previous page.